## Product Backlog
SSPMS — Product Backlog
Colour legend: 🔴 Must Have 🟡 Should Have 🔵 Could Have 🟢 Done 🔷 In Progress 🟠 Blocked
ID | Epic | Feature | Priority | SP | User Story | Acceptance Criteria | Sprint | Status | Assignee
PB-001 | Authentication | JWT Login | Must Have | 5 | As a user, I want to log in with my email and password so that I can access my role-specific dashboard. | • Valid credentials issue JWT + refresh token • Invalid credentials return 401 • Role claim included in token • Token expires in 60 min • Refresh token valid 7 days | Sprint 1 | Done | Saksham Tapadia
PB-002 | Authentication | 2FA TOTP | Should Have | 3 | As a user, I want to enable TOTP two-factor authentication so that my account is protected from unauthorised access. | • GET /auth/2fa/enable returns TOTP URI • PATCH /auth/2fa/verify activates 2FA • Login requires TOTP code when enabled • PATCH /auth/2fa/disable requires password • Invalid TOTP returns 400 | Sprint 1 | Done | Saksham Tapadia
PB-003 | Authentication | Password Reset OTP | Must Have | 3 | As a user, I want to receive a one-time password by email so that I can reset my forgotten password. | • POST /auth/forgot-password sends OTP email • OTP expires in 15 minutes • POST /auth/reset-password validates OTP and updates hash • Used OTP cannot be reused • Email not revealed if not found | Sprint 1 | Done | Ayush Mathur
PB-004 | Authentication | Token Refresh | Must Have | 2 | As a user, I want my session to stay active so that I am not unexpectedly logged out while working. | • POST /auth/refresh issues new access token • Old refresh token is revoked on use • Expired/invalid refresh token returns 401 • Frontend auto-refreshes on 401 intercept | Sprint 1 | Done | Saksham Tapadia
PB-005 | User Management | Create Users (Admin) | Must Have | 3 | As an admin, I want to create Trainer and Employee accounts so that I can onboard new team members. | • POST /users returns 201 with user record • Temporary password emailed on creation • Role must be Trainer or Employee • Duplicate email returns 400 • Only Admin role can create users | Sprint 1 | Done | Ayush Mathur
PB-006 | User Management | Profile Management | Should Have | 2 | As a user, I want to update my profile name and avatar so that my information is current. | • PUT /users/me/profile updates name and avatarUrl • GET /users/me returns current profile • Avatar URL validated as URL format • Name must be 2–100 characters | Sprint 1 | Done | Diya Garg
PB-007 | User Management | Deactivate User | Must Have | 1 | As an admin, I want to deactivate user accounts so that I can revoke access without deleting records. | • PATCH /users/{id}/deactivate returns 204 • Deactivated user cannot log in (401) • Admin only endpoint • Cannot deactivate own account | Sprint 1 | Done | Ayush Mathur
PB-008 | Class Management | Create Classes | Must Have | 3 | As a trainer, I want to create classes with skill tags so that I can organise employees by learning objectives. | • POST /classes returns 201 • Name, description, skill tags, start/end date required • SkillTags stored as comma-separated string • Only Trainer/Admin can create classes | Sprint 2 | Done | Aman Nahar
PB-009 | Class Management | Enroll Employees | Must Have | 2 | As a trainer, I want to enrol employees into my class so that they can access assigned tasks. | • POST /classes/{id}/enroll returns 204 • Duplicate enrolment returns 400 • Employee must exist and be active • Enrolment status defaults to Active | Sprint 2 | Done | Aman Nahar
PB-010 | Class Management | Announcements | Should Have | 2 | As a trainer, I want to post announcements to my class so that all enrolled employees are informed of updates. | • POST /classes/{id}/announcements returns 201 • Announcement delivered via SignalR in real time • GET /classes/{id}/announcements lists history • Only trainer of that class can post | Sprint 2 | Done | Diya Garg
PB-011 | Task Management | Create MCQ & Code Tasks | Must Have | 5 | As a trainer, I want to create tasks with MCQ and open-ended code questions so that I can assess employees comprehensively. | • POST /tasks returns 201 • Questions support MCQ (with options) and Code types • Each question has marks allocation • Task saved in Draft status initially • Min 1 question required to publish | Sprint 2 | Done | Saksham Tapadia
PB-012 | Task Management | Task Scheduling | Must Have | 2 | As a trainer, I want tasks to have a start time, end time and duration so that the exam window is clearly defined. | • StartAt, EndAt, DurationMinutes fields required • EndAt must be after StartAt • Duration cannot exceed EndAt − StartAt • Task is visible to employees only after StartAt | Sprint 2 | Done | Aman Nahar
PB-013 | Task Management | Publish Tasks | Must Have | 1 | As a trainer, I want to publish tasks so that enrolled employees can see and attempt them. | • PATCH /tasks/{id}/publish returns 204 • Status changes Draft → Published • Notification sent to all enrolled employees • Published tasks cannot be edited | Sprint 2 | Done | Aman Nahar
PB-014 | Submissions | Start Submission | Must Have | 3 | As an employee, I want to start a task and see a countdown timer so that I know how much time remains. | • POST /tasks/{id}/start returns submission with timer info • Pre-creates answer slots for all questions • Returns existing draft if already started • Validates task is Published and within window | Sprint 3 | Done | Saksham Tapadia
PB-015 | Submissions | Auto-Save Draft Answers | Must Have | 2 | As an employee, I want my answers to be saved automatically so that I do not lose progress if my browser crashes. | • PATCH /submissions/{id}/save-draft returns 200 • Partial answers accepted • No submission status change on save • Client auto-saves every 30 seconds | Sprint 3 | Done | Aman Nahar
PB-016 | Submissions | Submit with Rank | Must Have | 5 | As an employee, I want to submit my task and receive a submission rank so that I know how I compared to peers. | • POST /submissions/{id}/submit returns submission with rank • Rank assigned atomically in Serializable transaction • MCQs auto-graded on submission • Multiplier applied based on rank • Cannot submit after deadline | Sprint 3 | Done | Saksham Tapadia
PB-017 | Submissions | Timer & Auto-Submit | Must Have | 3 | As the system, I want to auto-submit tasks when their deadline expires so that fairness is maintained for all employees. | • Background job runs every minute • Expired tasks change status to Closed • Draft submissions become Submitted with zero multiplier • Zero-score submissions created for no-shows • IsAutoSubmitted flag set on forced submissions | Sprint 3 | Done | Saksham Tapadia
PB-018 | Submissions | Malpractice Detection | Must Have | 3 | As a trainer, I want the system to detect tab switching during a task so that I can identify potential academic integrity violations. | • Frontend monitors visibility change events • Tab switch count incremented per switch • >3 tab switches triggers auto-submit • IsMalpractice and TabSwitchCount recorded • Trainer notified via in-app notification • Malpractice submissions score zeroed | Sprint 3 | Done | Aman Nahar
PB-019 | Evaluation | Manual Evaluation | Must Have | 5 | As a trainer, I want to manually score open-ended answers and add evaluator notes so that employees receive fair, detailed feedback. | • PUT /submissions/{id}/evaluate scores all answers • Multiplier applied to each raw score • Plagiarism flag zeroes individual answer score • Status changes Submitted → Evaluated • Employee notified with final score • Email confirmation sent | Sprint 3 | Done | Diya Garg
PB-020 | Evaluation | Plagiarism Flag | Must Have | 2 | As a trainer, I want to flag individual answers as plagiarism so that the score is zeroed without affecting the raw record. | • PATCH /submissions/answers/{id}/plagiarism-flag toggles flag • Flagged answers: FinalScore = 0 • Unflagged answers: FinalScore restored • Submission total recalculated | Sprint 3 | Done | Diya Garg
PB-021 | Evaluation | Bulk Complete Evaluation | Should Have | 1 | As a trainer, I want to bulk-complete evaluation for MCQ-only tasks so that I do not have to evaluate each submission manually. | • POST /tasks/{id}/bulk-complete-evaluation changes all Submitted → Evaluated • Only applicable when all questions are MCQ • Employees notified in bulk • Returns count of submissions updated | Sprint 3 | Done | Diya Garg
PB-022 | Gamification | XP & Leaderboards | Must Have | 5 | As an employee, I want to earn XP points for task performance and see my rank on the leaderboard so that I am motivated to improve. | • XP awarded on evaluation: finalScore × XP multiplier • XP ledger records every transaction • GET /leaderboards/{classId} returns rankings • Filter by week / month / all-time • Redis cached for 60s TTL | Sprint 4 | Done | Saksham Tapadia
PB-023 | Gamification | Badge System | Should Have | 5 | As an employee, I want to earn badges for achievements so that my milestones are recognised and displayed on my profile. | • 8+ badge types: First Submission, Speed Demon, Perfectionist, Streak, Scholar, Team Player, Malpractice-Free, Top Scorer • Badges awarded automatically after submission/evaluation • GET /badges/user/{id} lists earned badges • GET /badges/dashboard/me returns profile summary | Sprint 5 | In Progress | Pankhuri
PB-024 | Analytics | Blind Spot Analysis | Must Have | 5 | As a trainer, I want to see per-question pass rates so that I can identify knowledge gaps and tailor my teaching. | • GET /analytics/{taskId}/blind-spots returns per-question stats • MCQ: pass = correct answer selected • Code: pass = ≥50% marks earned • <50% pass rate flagged as blind spot • Heatmap visualisation in dashboard | Sprint 4 | Done | Saksham Tapadia
PB-025 | Analytics | Code Similarity Radar | Must Have | 8 | As a trainer, I want to detect plagiarism clusters across code submissions so that I can identify collusion groups. | • Jaccard token similarity computed pairwise • >72% similarity triggers flag • Risk levels: Low (72–80%), Medium (80–90%), High (>90%) • Union-Find clusters suspected pairs into groups • GET /analytics/{taskId}/similarity returns matrix + clusters | Sprint 4 | Done | Saksham Tapadia
PB-026 | Analytics | Performance Velocity | Must Have | 5 | As an employee, I want to see my performance trend and a predicted next score so that I can understand my learning trajectory. | • Linear regression on last 6 normalised scores • Trend: Rising (slope >3%), Falling (<−3%), Stable • Predicted next score = last_score + slope • GET /analytics/velocity/{employeeId} returns trend data • Trend arrow displayed on leaderboard | Sprint 4 | Done | Saksham Tapadia
PB-027 | Reports | PDF & Excel Reports | Must Have | 5 | As a trainer, I want to export performance reports as PDF or Excel so that I can share insights with stakeholders. | • GET /reports/{taskId}?format=pdf¦excel returns file • GET /reports/me returns employee self-report • QuestPDF used for PDF, ClosedXML for Excel • Reports cached in Redis for 5 minutes • Includes scores, ranks, trend, badges | Sprint 5 | Done | Saksham Tapadia
PB-028 | Notifications | Real-Time Notifications | Must Have | 5 | As a user, I want to receive real-time notifications for task events so that I am always informed without refreshing the page. | • SignalR NotificationHub delivers push notifications • Events: task published, results ready, badge earned, malpractice • Notification bell shows unread count • GET /notifications returns history • PATCH /notifications/{id}/read marks as read | Sprint 5 | Done | Aman Nahar
PB-029 | Security | Rate Limiting & Audit Logs | Must Have | 3 | As the system, I want auth endpoints to be rate-limited and all user actions to be audited so that security and compliance are maintained. | • Auth endpoints: 10 requests/minute fixed window • Exceeding limit returns 429 • AuditLog records: userId, action, timestamp, IP • Login success/failure logged • Admin can view audit trail | Sprint 5 | Done | Ayush Mathur
PB-030 | DevOps | CI/CD Pipeline | Should Have | 3 | As the team, I want a GitHub Actions CI pipeline so that every pull request is validated automatically before merge. | • Workflow: dotnet build + test, ng build • Pipeline runs on every PR to develop/main • Branch protection blocks merge if CI fails • Build status badge in README • Secrets stored in GitHub Actions secrets | Sprint 5 | Done | Ayush Mathur

## User Stories
SSPMS — User Stories (Detailed)
ID | Title | As a… | I want to… | So that… | SP | Acceptance Criteria | Technical Notes
US-001 | JWT Authentication | a user (employee, trainer, or admin) | log in with my email and password and receive a JWT access token | I can securely access my role-specific dashboard and API resources | 5 | 1. Valid credentials → 200 with access token, refresh token, expiresIn, user profile 2. Invalid credentials → 401 Unauthorized (no detail leak) 3. Inactive account → 401 4. Token contains claims: userId, email, name, role, jti 5. Access token expires in 60 minutes 6. Refresh token valid 7 days and hashed in DB | POST /api/v1/auth/login JWT signed with HMAC-SHA256 BCrypt.Verify for password comparison Rate limited: 10 req/min per IP RefreshToken row created on every login
US-002 | Two-Factor Authentication | a security-conscious user | enable TOTP-based two-factor authentication on my account | my account is protected even if my password is compromised | 3 | 1. GET /auth/2fa/enable returns otpauth:// URI for QR code 2. PATCH /auth/2fa/verify activates 2FA after confirming code 3. Subsequent logins require a valid TOTP code 4. Invalid TOTP → 400 Bad Request 5. PATCH /auth/2fa/disable requires current password 6. VerificationWindow(2,2) allows 60-second clock skew | OtpNet library (Totp class) Secret stored as Base32 in User.TwoFASecret TwoFAEnabled boolean flag on User entity
US-003 | Class Management | a trainer | create and manage skill-based classes | I can organise employees by learning objectives and assign targeted tasks | 5 | 1. POST /classes creates class → 201 with class record 2. Name, description, skill tags and date range required 3. POST /classes/{id}/enroll adds employee → 204 4. Duplicate enrolment → 400 5. GET /classes/{id}/enrollments lists enrolled employees 6. Trainer can post announcements with real-time SignalR delivery | ClassEnrollment entity with EnrollmentStatus enum SkillTags stored as comma-separated string on AssignedTask AnnouncementHub broadcasts to class group DateOnly used for start/end dates
US-004 | Task Creation | a trainer | create tasks containing MCQ and open-ended code questions with configurable marks | I can assess both theoretical knowledge and practical coding skills in one task | 5 | 1. POST /tasks creates task in Draft status → 201 2. QuestionType: MCQ ¦ Code 3. MCQ questions include up to 6 option choices with one correct answer 4. Code questions have marks but no options 5. Task must have start/end time and duration in minutes 6. PATCH /tasks/{id}/publish changes status Draft → Published → 204 7. Published task visible to enrolled employees after StartAt | AssignedTask entity with AssignmentStatus enum Question and MCQOption child entities Email notification sent to enrolled employees on publish Task cannot be edited after publishing
US-005 | Task Submission | an employee | start a task, auto-save my answers, and submit when ready | I receive a submission rank that reflects how quickly and accurately I completed the task | 8 | 1. POST /tasks/{id}/start → 200 with submission + timer data 2. Existing draft returned if already started 3. PATCH /submissions/{id}/save-draft persists partial answers → 200 4. POST /submissions/{id}/submit finalises submission → 200 5. Submission rank assigned atomically (Serializable isolation) 6. MCQ answers auto-graded on submit 7. Multiplier applied: Rank 1 = 1.5×, Rank 2–5 = 1.2×, others = 1.0× 8. Cannot submit after task EndAt | Serializable transaction via CreateExecutionStrategy().ExecuteAsync() SqlServerRetryingExecutionStrategy required for retry logic Submission.SubmissionRank = COUNT(non-draft) + 1 at commit time SignalR pushes live submission count update to trainer
US-006 | Auto-Submit on Deadline | the system | automatically close expired tasks and force-submit any outstanding drafts | no employee can gain an unfair advantage by submitting after the window closes | 3 | 1. Background job runs every 60 seconds 2. Tasks with EndAt < now and status = Published → Closed 3. Draft submissions → Submitted with IsAutoSubmitted = true, Multiplier = 0 4. Enrolled employees with no submission → zero-score Submitted record created 5. No notification sent for auto-submissions | ExpiredSubmissionsJob : BackgroundService Runs via IHostedService in Program.cs Queries ClassEnrollments to find employees who never started
US-007 | Malpractice Detection | a trainer | be notified when an employee switches tabs excessively during a task | I can identify potential academic integrity violations and take appropriate action | 3 | 1. Frontend monitors document.visibilitychange events 2. Switch count incremented and displayed as warning to employee 3. After 3 switches the task is auto-submitted via POST /submissions/{id}/submit-malpractice 4. IsMalpractice = true, TotalFinalScore = 0 5. Trainer receives in-app notification with employee name and switch count 6. Malpractice flag visible in trainer evaluation view | MalpracticeSubmitRequest(tabSwitchCount) All answer FinalScores zeroed regardless of raw score NotificationService sends alert to task.CreatedByTrainerId
US-008 | Manual Evaluation | a trainer | manually score open-ended answers, flag plagiarism, and submit final grades | employees receive accurate, fair scores with detailed feedback | 5 | 1. GET /submissions/{taskId}/all lists all submissions for a task 2. PUT /submissions/{id}/evaluate accepts per-answer scores and notes 3. Multiplier applied to raw score for final score 4. Plagiarism-flagged answers receive FinalScore = 0 5. Submission status changes Submitted → Evaluated 6. Employee receives in-app notification + email with final score 7. PATCH /submissions/answers/{id}/plagiarism-flag toggles flag independently | EvaluateSubmissionRequest with per-answer EvaluateAnswerItem IsPlagiarismFlag on SubmissionAnswer entity POST /tasks/{id}/bulk-complete-evaluation for MCQ-only tasks
US-009 | XP & Leaderboard System | an employee | earn experience points for every evaluated task and see my rank on the class leaderboard | I am motivated to perform consistently and can track my standing relative to peers | 5 | 1. XP awarded on evaluation: TotalFinalScore × 10 (configurable) 2. XP ledger records every transaction with source 3. GET /leaderboards/{classId} returns ranked list 4. Filter: week ¦ month ¦ all-time 5. Leaderboard cached in Redis for 60 seconds 6. Employee can see personal XP total on dashboard | XPLedger entity: employeeId, amount, source, taskId, earnedAt Redis IDistributedCache with TTL = 60s Leaderboard sorted by TotalXP desc, then SubmittedAt asc for ties
US-010 | Blind Spot Analysis | a trainer | see per-question pass rates across all submissions so that I can identify questions where the class struggled | I can tailor my teaching to address specific knowledge gaps efficiently | 5 | 1. GET /analytics/{taskId}/blind-spots returns per-question stats 2. MCQ pass = correct answer selected 3. Code/Assessment pass = ≥50% of question marks earned 4. Pass rate = passes / total attempts × 100% 5. Questions with <50% pass rate flagged as 'blind spots' 6. Response includes question text, pass rate, total attempts 7. Heatmap visualisation in Angular trainer dashboard | Calculated on demand (no caching — real-time accuracy needed) Joins Question, SubmissionAnswer, Submission tables Only Submitted/Evaluated submissions counted
US-011 | Code Similarity Radar | a trainer | detect similar code submissions and identify potential plagiarism clusters | I can act on academic misconduct with evidence rather than guesswork | 8 | 1. GET /analytics/{taskId}/similarity returns pairwise matrix + clusters 2. Tokenise code: lowercase, strip punctuation, filter tokens <2 chars 3. Jaccard similarity = ¦A∩B¦ / ¦A∪B¦ 4. Threshold >72% triggers investigation flag 5. Risk levels: Low (72–80%), Medium (80–90%), High (>90%) 6. Union-Find algorithm clusters connected pairs into groups 7. Cluster size ≥3 highlighted as potential collusion ring | Implemented in AnalyticsService.GetSimilarityAsync() O(n²) pairwise comparison — acceptable for class sizes <200 Union-Find with path compression for cluster detection
US-012 | Performance Velocity Tracker | an employee | see my performance trend over recent tasks and a prediction of my next score | I can understand whether I am improving or declining and take corrective action | 5 | 1. GET /analytics/velocity/{employeeId} returns trend data 2. Uses last 6 normalised scores (score / totalMarks × 100) 3. Linear regression: slope = (ΣXY − nX̄Ȳ) / (ΣX² − nX̄²) 4. Trend: Rising (slope >3%), Falling (<−3%), Stable 5. Predicted next score = last_score + slope (clamped 0–100) 6. Line chart with regression line in Angular employee dashboard 7. Trend arrow and badge shown on leaderboard entry | Returns at minimum 2 data points; returns null if <2 submissions Normalised scores prevent marks-scale distortion Prediction is indicative only — displayed with caveat
US-013 | Report Generation | a trainer | export detailed performance reports as PDF or Excel for my class | I can share actionable insights with stakeholders and HR without manual data entry | 5 | 1. GET /reports/{taskId}?format=pdf downloads QuestPDF report 2. GET /reports/{taskId}?format=excel downloads ClosedXML workbook 3. Report includes: summary stats, per-employee scores, ranks, trends 4. GET /reports/me returns employee self-report (own data only) 5. Reports cached in Redis for 5 minutes (cache key = taskId+format+role) 6. PDF generation <10s for 200 employees × 50 tasks | QuestPDF v2025.1.0 for PDF layout ClosedXML for Excel workbook IReportService injected into ReportsController Redis IDistributedCache with 5-minute TTL

## Sprint Backlog
SSPMS — Sprint 5 Backlog ¦ 2026-03-09 → 2026-03-21
Sprint Goal: Deliver production-ready reporting, real-time notifications, security hardening, and CI/CD pipeline. Complete gamification badge UI and pass OWASP ZAP scan.
Task ID | PB Ref | Description | Assignee | Story Points | Hours Est. | Hours Act. | Status | Blocker / Notes
TASK-101 | PB-027 | Implement PDF report service with QuestPDF — layout, employee section, score table, totals | Saksham Tapadia | 5 | 8 | 7.5 | Done
TASK-102 | PB-027 | Implement Excel report service with ClosedXML — multi-sheet workbook, styling | Saksham Tapadia | 3 | 5 | 5 | Done
TASK-103 | PB-027 | Expose report download API endpoints: GET /reports/{taskId} (trainer) + GET /reports/me (employee) | Saksham Tapadia | 2 | 3.5 | 3.5 | Done
TASK-104 | PB-027 | Redis caching for generated reports — 5-minute TTL, cache-key strategy per taskId+format+role | Ayush Mathur | 2 | 3 | 3 | Done
TASK-105 | PB-027 | Angular employee report page — download buttons (PDF/Excel), preview summary card | Pankhuri | 3 | 5 | 5 | Done
TASK-106 | PB-024/025/026 | Angular trainer analytics dashboard — Blind Spot heatmap, Similarity matrix, Velocity line chart | Pankhuri | 5 | 9 | 9 | Done
TASK-107 | PB-028 | Real-time submission counter during task attempt — SignalR SubmissionHub integration | Aman Nahar | 3 | 5 | 5 | Done
TASK-108 | PB-028 | Notification bell component — unread badge count, real-time delivery via SignalR | Aman Nahar | 3 | 5 | 5 | Done
TASK-109 | PB-028 | Notification history page — list all notifications, mark read, filter by unread | Diya Garg | 2 | 4 | 4 | Done
TASK-110 | PB-029 | Rate limiting on auth endpoints — fixed window 10 req/min, 429 response | Ayush Mathur | 2 | 3 | 3 | Done
TASK-111 | PB-029 | Audit log service — record Login.Success/Failed, action logs, admin viewer stub | Ayush Mathur | 2 | 4 | 4 | Done
TASK-112 | PB-029 | OWASP ZAP security scan — run full scan against staging, triage findings | Ayush Mathur | 3 | 5 | — | Blocked | Team lacks OWASP ZAP training — carry over to Sprint 6
TASK-113 | PB-030 | GitHub Actions CI pipeline — dotnet build+test, ng build, status badge in README | Ayush Mathur | 3 | 5 | 5 | Done
TASK-114 | PB-023 | Badge system UI — dashboard/me page, earned badge cards, unlock animations | Pankhuri | 1 | 3.5 | 3.5 | In Progress | 70% complete — 3 badge types still missing UI variant
SPRINT SUMMARY
Total Story Points | 39
Completed (Done) | 35 (89%)
Remaining | 4
Hours Estimated | 68.0
Hours Actual | 62.5
Sprint Velocity (avg last 3) | 41
Team | Saksham Tapadia, Ayush Mathur, Aman Nahar, Diya Garg, Pankhuri

## Sprint Review
SSPMS — Sprint 5 Review ¦ 2026-03-09 → 2026-03-21
Sprint Goal: Deliver production-ready reporting, real-time notifications, security hardening, and CI/CD pipeline. Complete gamification badge UI and pass OWASP ZAP scan.
✅ Completed & Accepted by Product Owner
User Story | Title | What was Demo'd | PO Decision | PO Feedback
US-009 | XP & Leaderboard System | Leaderboard with 3 time-filter views, XP ledger, Redis caching | Accepted ✓ | Leaderboard is impressive — exactly what we envisioned. Redis TTL is smart.
US-010 | Blind Spot Analysis | Per-question pass rates with heatmap, <50% flagged as blind spot | Accepted ✓ | This will transform how we teach. Game-changer feature — ship it!
US-011 | Code Similarity Radar | Jaccard similarity matrix, Union-Find clustering, 3 risk levels | Accepted ✓ | Love the cluster visualisation. Flag everything above 80% for review.
US-013 | Report Generation | PDF (QuestPDF) + Excel (ClosedXML), Redis-cached 5 min, self-service | Accepted ✓ | PDF looks professional. Excel is perfect for sharing with HR.
⚠️ Carryover Items (not completed this sprint)
PB / Task ID | Item | Status | Resolution
PB-023 | Badge System UI | In Progress — 70% complete (5 of 8 badge types have UI, 3 remaining) | Carry over to Sprint 6 — target: complete by Sprint 6 Day 4
TASK-112 | OWASP ZAP Security Scan | Blocked — team lacks OWASP ZAP training; scan not yet executed | Carry over to Sprint 6 — schedule training in first 2 days
📊 Sprint Metrics
Sprint Goal Achievement | 90% (38 / 42 story points completed)
Stories Accepted by PO | 4 of 5 demonstrated
Sprint Velocity (this sprint) | 38 SP
Rolling Average Velocity (last 3) | 41 SP
Defects found in sprint | 2 (SMTP error 500, EF transaction exception) — both fixed
Team Satisfaction | 4.2 / 5.0
Sprint Date | 2026-03-09 → 2026-03-21

## Sprint Retrospective
SSPMS — Sprint 5 Retrospective ¦ 2026-03-09 → 2026-03-21
✅ What Went Well
# | Topic | Details
1 | SignalR integration | Real-time submission counter and notification bell worked flawlessly on first demo. No race conditions.
2 | Analytics features | Blind Spot, Similarity Radar, and Velocity Tracker all shipped together — PO called them 'game-changers'.
3 | Team collaboration | No blocker lasted more than half a day. Team unblocked each other quickly without escalation.
4 | CI/CD pipeline | GitHub Actions caught two build-breaking changes before they hit develop. Saved hours of debugging.
5 | Clean architecture | Adding the analytics layer required zero changes to existing controllers — DI and interfaces paid off.
❌ What Didn't Go Well
# | Topic | Details
1 | UI underestimated | Angular analytics dashboard took 50% more time than estimated (9h actual vs 9h estimated). Heatmap layout was tricky.
2 | OWASP ZAP blocked | No team member has completed OWASP ZAP training. Should have been addressed in Sprint 4.
3 | Security warnings found late | NuGet CVEs (AutoMapper, MailKit) were discovered during sprint, not at dependency update time.
4 | Angular state messy | Sharing task state between task-attempt and submission components required prop drilling. No state manager.
5 | No QA pass | Sprint ended with no dedicated QA time. Bugs were caught in demo, not before.
🎯 Action Items for Sprint 6
ID | Action | Owner | Due Date | Priority
A-01 | Re-estimate UI stories using reference tasks (use TASK-106 as baseline) | Pankhuri | 2026-03-28 | High
A-02 | Complete OWASP ZAP online training (PortSwigger Web Security Academy) | Ayush Mathur | 2026-04-01 | High
A-03 | Add OWASP ZAP scan step to CI pipeline (fail on critical findings) | Saksham Tapadia | 2026-03-28 | High
A-04 | Spike: NgRx vs Akita for Angular state management — present findings in next planning | Aman Nahar | 2026-04-04 | Medium
A-05 | Allocate last 2 days of Sprint 6 as dedicated QA time (no new features) | Diya Garg | 2026-04-10 | High
A-06 | Create Angular component storybook for design consistency | Pankhuri | 2026-04-15 | Low
🏅 Team Shoutouts
# | Team Member | Recognition
1 | Saksham Tapadia | Architected the entire analytics engine (3 unique features) while maintaining system integrity and code quality standards throughout the sprint.
2 | Aman Nahar | Delivered flawless SignalR real-time features with zero production issues. Submission counter and notification bell worked on first demo.
3 | Pankhuri | Brought a SaaS-quality design vision to the trainer dashboard. The analytics visualisations look genuinely professional.
4 | Diya Garg | Completed the evaluation system ahead of schedule with zero bugs. The plagiarism flag UI is clean and intuitive.
5 | Ayush Mathur | Sprint's go-to debugger. Unblocked teammates on CI config, rate-limiting middleware, and audit log — without anyone having to ask twice.
📊 Overall Sprint Health
Sprint Health | 🟢 Healthy
Team Morale | 4.2 / 5.0 ⭐⭐⭐⭐
Technical Debt | Low — clean architecture maintained
Process Adherence | Conventional Commits followed, PRs reviewed within 24h
Carry-Forward Risk | Medium — OWASP ZAP and badge UI both need Sprint 6 attention
Recommendation for Sprint 6 | Focus on QA pass, OWASP scan, and completing badge system before adding new features